## 2017-2022 Action Plan
Resource & Waste Education Strategy & Action Plan for Devon Schools (2017-22)
The Resource & Waste Education Strategy and Action Plan for Devon Schools are supplementary documents produced in fulfilment of the Waste and Resource Management Strategy for Devon (2013)
This Action Plan is a working document covering the period 2017-2022.
Partners for the Stratgey include: Devon County Council, Torbay Council and the Devon Waste Collection Authorities.
The provision of the Devon Waste Educators is an important and significant element in the delivery of the Action Plan.
Aim: | To promote and encourage learning and practical action to reduce waste and improve resource efficiency in Devon's schools and their surrounding communities.
Objectives: | 1. To help children to actively learn about waste reduction and resource efficiency.
2. To help schools engaged with the intensive programme reduce their residual waste by 10% by 2022
3. To enable and support at least 40 schools to reduce their food waste and to compost on site by 2022
4. To enable 100% of schools to recycle at least four main material streams by 2022
5. To work with schools and support them to actively engage with their local communities on waste reduction and resource efficiency
6. To provide signposting, training, resources and regular service delivery updates for strategy partners and schools
To support the aim and objectives of this strategy, DCC and partners will:-
Seek 15% supplementary funding to support the ongoing delivery of this strategy by 2022
Consult with relevant partners & schools to ensure 2017-2022 Strategy update remains relevant and effective
Review the strategy action plan annually
Update the strategy in 2022
1.0 - Strategy & Management
| Action | Objective | Outcome | Evaluation | Responsibility | Resource | Progress (RAG)
1.1 | Monitor the effectiveness of the Waste Education Strategy through quantitative and qualitative evaluation and reliable data collation | 1 - 6 | Evidence shows that delivery of the Waste Education Strategy offers a cost effective behavioural change mechanism which reduces costs for schools and local authorities. The strategy also helps to improve recycling performance in schools and the wider community. Delivery of the strategy increases recycling rates and reduces contamination level at school and community level. The strategy improves understanding and awareness of waste reduction and resource efficiency. | Quantitative data from waste audits, waste budget analysis and waste collection tonnage data will be supported by qualitative data sourced from awareness surveys, impact assessment reports and direct delivery feedback | All Partners | Monitoring and evaluation forms a component of the existing Devon Waste Educators contract. Partners will also evaluate and contribute to delivery of this action representing time demand rather than cost consideration | Green
1.2 | Maintain the continuity of waste education in Devon's schools through 3+ years contract terms for at least 1.5 full time equivalent 'Waste Educators' (Subject to avaialble funding) | 1 - 6 | Schools benefit from on-going support to help children to learn how to reduce waste and improve resource efficiency within the wider sustainability agenda leading to fuller engagement with the programme and embedded sustainable change and improved awareness and management practices within schools. | The Devon Waste Educators Contract is being retendered in 2017 for a 3 +2 year term for at least 1.5 FTE Waste Educators. | DCC | DCC Waste Education budget and external sources where available | Green
1.3 | Waste Educators will provide partners with regular service delivery updates. Partners will support Waste Educators to deliver waste education in their areas and update educators with local service changes as appropriate | 6 | Strategy partners are engaged with the programme and relevant information is disseminated to schools and partners | Feedback from Waste Educators and Partners at Officers Forum | Waste Educators & all Partners | Waste Eductors & Partners staff time | Green
1.4 | Support training and development needs of partners and school staff (e.g: heads & governors, teachers, support staff & parent helpers) to encourage the school community to embed good practice for sustainable waste management in Devon's schools | 6 | All partners and school staff are inspired to share and deliver good sustainability waste management practice in Devon's schools leading to engaged pupils throughout the partnership area | Number of events held & feedback from attendees. | All partners & Waste Educators | DCC Waste Education budget | Green
1.5 | Review the existing centralised database for school activities, visits and other educational provision in Devon provided by partners | - | A reliable record of school and partnership activities and visits enables a full understanding of current service provision and levels of schools engagement. Partners are able to access relevant summary information by arrangement. | Accurate and reliable records result in better monitoring and evaluation | DCC | DCC Waste Education budget and staff time | Amber
1.6 | Ensure that proposals for new waste management facilities consider safe opportunities for community and school site visits | - | All suitable waste management facilities within the partnership area allow opportunities for site visits for schools and their communities. Facilities provide safe access routes, meeting / education rooms and parking to facilitate larger vehicles such as coaches | Facilities constructed and number of site visits monitored | DCC & Partners | Strategy Partners and infrastructure providers | Green
2.0 Curriculum
2.1 | Develop and deliver a comprehensive range of interactive and inspiring workshops/activities and events about waste reduction and resource efficiency that support the school curriculum and the Waste and Resource Management Strategy for Devon. | 1-6 | All workshops and activities where appropriate are linked to aspects of the National Curriculum including Science, Geography & Citizenship. Pupils develop a broad understanding of issues regarding waste reduction and resource efficiency, leading to an engaged Devon population contributing to the ambitions contained in the Waste and Resource Management Strategy for Devon | Gather feedback on the effectiveness of the curriculum based activities from both teaching staff and pupils. | DCC & Waste Educators | DCC Waste Education budget and staff time | Green
2.2 | Provide educational school visits to waste management facilities | 1 | Children gain first hand experience of the waste management industry, and understand what happens to waste in Devon, experiencing the sites, sounds and smells! | Number of school visits held each year and feedback from teachers and pupils. | DCC, Waste Educators & partners | DCC Waste Education budget and staff time | Green
2.3 | Develop educational resources to promote waste reduction and resource efficiency through the school 'Zone' website | 1-6 | Online resources support physical delivery leading to greater autonomy for schools to deliver follow-on work and embed sustainable practices in their school | A range of curriculum linked supporting documents, advice and interactive resources are hosted on the school 'Zone' website | DCC & Waste Educators | DCC waste education budget and staff time | Green
2.4 | Review the schools 'Zone' website' to ensure it is meeting the needs of pupils and teaching staff. | 1-6 | The' Zone' website is the principal source of waste information for Devon's schools and contains succinct topic summaries supporting the actions in this strategy. The website is accessible, interactive and written in plain English | Increase website traffic to the at school 'Zone' website through better promotion. Analytics is built into the 'Zone' website enabling consistent and reliable data analysis by page | DCC | DCC waste education budget and staff time | Green
2.5 | Develop follow up work for teachers to use in class or as homework to extend learning beyond the initial partner input | 1 & 5 | Teachers are able to access follow up activities via the school 'Zone' website or Waste Educators to support further independent learning in the classroom or at home | Number of request/downloads for follow up work recorded | DCC & Waste Educators | DCC & partners staff time | Green
3.0 Campus
| Action | Objective | Outcome | Evaluation | Responsibility | Resource | Progress (RAG)
3.1 | Maintain a wide range of relevant guides and information to promote waste reduction and efficient use of resources in schools and their wider communities | 1 - 6 | Schools are supported with a wide range of good practice guides linked to strategy actions such as information on how the school can reduce waste and save money. | Good practice guides are available, or signposted, from the at school 'Zone' website | DCC | DCC waste education budget and staff time | Green
3.2 | Provide practical support for schools to help them reduce their waste and improve recycling and composting performance | 2 - 4 | Devon Schools have access to practical support from partners to assist effective delivery of 3Rs initiatives. | Waste audit, cost data and case studies will monitor the outcome of action planning and delivery. | All Partners | Partners staff time | Green
3.3 | Work with schools to achieve a 10% reduction in waste sent for disposal (intensive schools programme only) | 2 | Schools engaged with the intensive programme are helped to reduce their waste sent for disposal using baseline waste audit data. Support is delivered through self help good practice guides, direct practical & educational support, following targeted action planning. Heads and Governors support efforts to reduce waste leading to a reduction in waste management costs and improved environmental performance and waste awareness in schools | Waste audit data provided by the intensive programme of the Waste Educators contract. | DCC, Waste Educators & partners | DCC waste education budget and staff time | Green
3.4 | Work with waste management providers and collection authorities to ensure that all schools have access to a recycling/composting collection service for at least four main material streams | 4 | All schools have access to adequate and appropriate recycling and / or composting collection services (or on-site composting) for at least four main waste streams such as food, paper, card, plastics or electronic and electrical equipment (WEEE) | Recycling and/or composting collections services in place and an up-to-date summary of materials collected from schools by district area in maintained. | DCC & Partners | WCA's - Operational implications (containers, collections, promotion & education) WDA - Recycling credit payments, possible disposal costs. Schools - Possible reduction in disposal costs. | Green
3.5 | Review and update MoUs between the WDA & WCA to ensure all Devon Schools have access to recycling collection services. | 4 | MOU's are renewed ensuring that every Devon school has the opportunity to draw on adequate local authority recycling collection services for specified materials. Schools are free to select LA or private sector providers | MOUs and supporting documents are updated and remain fit for purpose | DCC & WCAs | Partners staff time | Amber
3.6 | Formalise a Service Level Agreement (SLA) between collection authorities and schools to clarify service provision, materials to be collected and responsibilities. | 4 | SLAs are considered 'best practice' and have been agreed and signed by all schools in receipt of LA waste collection services. This leads to consistent, more flexible services, increased recycling and reduced contamination levels through partnership and LA support | SLAs between schools and WCA signed and fit for purpose. | WCAs | WCA Staff time | Amber
3.7 | To enable and support at least 40 schools to reduce their food waste and compost on site by 2022 | 3 | Food waste is reduced and the schools are successfully utilising an appropriate size and type of composting system on-site resulting in behavioural change benefits and curriculum support (e.g. science) | The number of composting schools is monitored | DCC, Waste Educators & partners | DCC waste education budget and staff time | Green
3.8 | Encourage Devon's schools to include relevant staff contract conditions which support sustainable waste practices in schools | 2 - 4 | All school staff with a responsibility for waste are supported to deliver effective recycling and composting schemes | Advice provided to schools on the Zone & through Intensive schools programme | DCC | Partners staff time | Amber
3.9 | Encourage greater reuse of Schools equipment by promoting WARPIt (online reuse portal) | 2, 5 & 6 | Increasing number of schools registered and actively using WARPIt | Number of schools registered & number of claims/donations using the system. | DCC | Staff time | Amber
3.1 | Signpost relevant resources, awards and funding opportunities for schools which support waste and sustainability issues | 6 | Devon's schools are aware and able to access a range of resources, awards and funding opportunities publicised on the 'Zone' web pages and via the Sustainability Bulletin. | The Zone website kept up to date & traffic to the site monitored. Number of Sustainability Bulletins published | DCC, Waste Educators & partners | Partners staff time | Green
4.0 Community
| Action | Objective | Outcome | Evaluation | Responsibility | Resource | Progress (RAG)
4.1 | Provide 'take home' sheets for pupils and parents containing targeted and practical approaches to reducing waste and resource efficiency in the home | 1 & 5 | Activity based take-home sheets are provided for all pupils following delivery of a Waste Educators workshops. Relevant and practical information is included for parents linked to authority specific schemes | Monitoring of distribution of take home sheets and feedback through 'prize draw' / competition elements of the sheets | All partners & Waste Educators | DCC waste education budget and partners staff time | Green
4.2 | Work with schools and support them to actively engage with their local communities on waste reduction and resource efficiency. | 5 | Schools host events for their wider community promoting sustainable waste & resource management e.g: uniform sale days, repair events, give & take events. | Number of events held | All partners & Waste Educators | Staff time | Green
4.3 | Support and encourage partnerships between schools and other organisations in their communities which contribute toward waste reduction and resource efficiency in both schools and their surrounding communities. | 5 | Schools are supported via a network of organisations linked by a common purpose to deliver waste reduction and resource efficiency in their communities | A broad framework of support and case studies are available and promoted on the at school 'Zone' website | All partners & Waste Educators | DCC & Partners | Green
Note on G24: sheilag: No sure what 'time demand rather than cost consideration' refers to
Note on B42: sheilag: Needs a key to explain abbreviations
Note on B51: sheilag: 'Reduction' doesn't need capital letter